## How to use this checklist
Recommendations and tips on using this checklist:-
1). First review the strategic decisions section to help bring to light key decisions that will then impact how you use the checklist.
2). We have covered some of the key departmental actions that need to be taken for health and safety, finance, staffing, marketing and operational. However, each business is different and we have created in this format so you can delete items that are not relevant and add where approproiate.
3). The checklist can be filtered by department for ease of use. You may want to share with each department head and have them amend actions as required.
4).We have assumed that operators will be opening in July timescales here and have focused this advice more towards bars, restaurants, pubs, food to go and coffee shops.
5). The "technology available" column is there to just highlight the tools Access can provide to help with these tasks, of course you may want to update with other techonlogy providers you use.

## Strategic Decisions
Here we take a look at some of the strategic questions you might want to discuss at Board or Owner level in order to help assist during the detailed planning stage using the checklist as a foundation.
We've split these into the four key categories hospitality operators will consider crucial to their business.
1). Customer | Things to consider
How are we going to keep our customers safe? | What will the new customer journey on premise look like? How can we maximise revenue but ensure customer safety and social distancing requirements New levels of health, safety and cleanliness will be required.
How are we going to communicate new plans to customers? | This goes beyond marketing - it is ensuring customers feel safe and secure in the new measures being implemented at every stage of the customer journey.
How are we going to continue to attract customers and fill (reduced capacity venues) in a new landscape?
How do we safely take payment from customers - is that by introducing cashless only payments? | Other options to reduce customer need for interaction with chip and pin such as order and pay at table.
How do we keep the hospitality, fun and the social element of our business alive whilst meeting social distancing requirements?
2). Staff | Things to consider
How are we going to keep our staff safe, and effectively share our new operating models and plans with them? | Do we provide PPE - what safety equipment will be compulsory or optional? What and how often will we require staff to confirm they are fit to work?
How do we instil them with the confidence to return to work? How do we manage shifts to ensure the return of as much of our workforce as possible? | Sharing plans with staff is key, but keeping feedback loop is also critical.
What do we need to do over the coming weeks and months to support staff returning onsite and those who are not comfortable or able to return?
How do we support staff, and pay staff who may need to isolate for 14 days due to new test and trace guidelines?
3). New business model and proposition | Things to consider
What will our business look like when it reopens - will we switch to more omni channel to include delivery, click & collect, retail, external catering, DIY menu packs etc. to support the reduction in on premise dining capacity? | Perhaps converting to a delivery model was not a viable option before lockdown due to the speed it happened, but it could be an additional revenue stream now. If you decide to run a delivery model before sites open understand the reasons for this - is it to make a profit, just to keep brand alive (to staff and customers) or to support charitable causes.
Do we need to review menus because of shortage of supplies and / or in order to keep chef numbers down (due to costs / social distancing in the kitchen)? If drink-led previously do we consider more food led offering?
Do we take this opportunity to re-evaluate our brand identity? What do we want to be known for? Sustainability and community focus will stay high on the agenda for customers so take time to review our proposition. | If decisions is to update brand values and proposition this will need to flow through all elements of the organisation from staff training, website and on premise to marketing promotion.
What pricing strategy do you want to take when reopening? Optimise volume at a lower price and perhaps follow promotional strategy or maintain prices but lower volume?
Will you open entire estate at once? Will some open for delivery pre July 4th target opening date? Go through the entire estate, site by site, and confirm what model will be adapted (delivery, dine-in etc.) and the predicted opening dates to enable better planning by the operations team. | Factors to consider will depend on whether you have outdoor space and size of venues. Some venues may not work with social distancing and plan to open at a much later stage.
What pricing strategy do you want to take when reopening? Optimise volume at a lower price and perhaps follow promotional strategy or maintain prices but lower volume.
4). Investment and liquidity | Things to consider
Do we need to re-capitalise business? What other funding options are available to us - this includes bank loans (backed by Government), crowd funding and new investors?
Do we need to consider restructuring the business? Options include CVA, liquidating various sites and buying back. | During planning stage, need to consider all options to ensure the business stays liquid during the coming weeks and months ahead and business returns to some sense of normality.

## Checklist
Task headline | Sub Category | Tasks | Additional information | Relevant (Y/N) | Department | Possible stage | Owner | Due date | Access Technology available | Comments
Staff planning & labour optimisation |  |  |  |  | HR | Stage 2 - Pre- opening
| Putting staff first | Start reaching out to furloughed staff to see how they feel about returning to work. | Some team members may experience anxiety about returning or have new childcare or caring challenges that didn't exist pre Covid. Ensure staff feel reassured if they want to take extended leave and that a job will be open to them afterwards - if possible**. |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Putting staff first | Schedule 1-2-1's with staff to discuss how they feel about returning, whether they will be coming back and if there are any specific needs, shift availability etc. that you need to consider. | It's likely that you may be bringing staff back in phases. Therefore, you could ask staff to volunteer on whether they want to return back within the first phase. Ensure that those who don't want to return back yet, because of genuine health & safety concerns, are managed sensitively. Use this process to identify staff within the 1.5 million high risk shielding that cannot currently return to work. |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Putting staff first | Create and share your "Covid-19" ready plan with staff. This should include what additional health and safety steps you'll be taking at a minimum. | Sharing this in advance of re-opening will help put staff at ease. |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Putting staff first | HR teams need to be creative in the way they engage employees and build a sense of team when there are less opportunities to do so; with streamlined teams on site and breaks likely to be staggered. Therefore, it may be worth keeping some of the virtual tactics you used during lockdown to enable your full team to stay connected. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Putting staff first | Staggered lunch breaks may need to be introduced to reduce staff interaction - consider lunch bags rather than sit down meals for groups of staff together. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Putting staff first | Talk to staff about how they will travel to work - can you stagger shifts to help staff avoid public transport, provide changing areas and storage space for cycling/running/walking to work? Also consider, whether you can offer free / subsidise parking or cycle / walk to work schemes. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Putting staff first | Ensure there is an open feedback loop from staff - and it's important to give them the opportunity to call out areas that you might be failing to deliver in regards to staff or customer health and safety. |  |  | HR | Stage 3 -Opening week (and beyond) |  |  | Access People
| Putting staff first | Create new staff guidance regarding the number of people allowed to be in the changing rooms / staff toilet areas at any one point. You may need to limit 1 staff member at a time in chilled or dry stores. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Company vision | If the brand, vision and culture being revised, HR will need to set out new staff communication strategy and training programmes to support. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Staff management | Update HR system and reverse furlough pay process. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Staff management | Update rotas and staff locations and ensure rotas have been submitted to staff. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Staff / rota management | Planning will need to go into each rota to ensure staff are taking sufficient breaks and may need shorter shifts as people have adjusted to more work / life balance during lockdown. May need staggered arrivals to help with transport. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Education | Staff education - ensure staff understand that if they undertake any foreign travel they will need to self-isolate for a period of 14 days upon return. |  |  | HR | Stage 5 - longer term
| Skills / certification | Track retraining, expired training requirements and report on minimum levels of mandatory requirements on site; this includes both legal requirements and best practice (e.g. ensuring that food hygiene certificates are up-to-date) – consider if you can reopen the site, if you do not have enough of each type of trained personnel. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Training | Staff may need refreshers on the day-to-day task management – consider how this can be tracked and reported on a daily / weekly basis. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Training | We may face new legislative training requirements – make sure your HR system can show compliance to the new standard. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Passwords | Review all tools and technology - make a list of new users to be added, permissions to be changed or individuals removed. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Bookings | Decide how you'll manage bookings pre-opening. Allocate at least one member of team to manage enquiries and levels based on viable table layouts. |  |  | HR | Stage 2 - Pre- opening |  |  | Access Collins
| Bookings | Consider tools to help automate calls for bookings - but again allocate a member of the team to accept or confirm bookings / enquiries. |  |  | HR | Stage 2 - Pre- opening |  |  | Access Collins
| Bookings | Ensure staff are trained on correct use of all protective equipment such as masks etc. |  |  | HR | Stage 4 - new normal |  |  | Access People
| Training | Quickly identify and allocate time for staff to complete new training - particularly around health and safety, managing guest and customer expectation in a post Covid-19 environment. |  |  | HR | Stage 4 - new normal |  |  | Access People
| Staff engagement | Identify or ask for staff volunteers to be part of a team or employee committee who can help management set new best practices – best ways to work whilst keeping social distancing measures in place; such as security procedures and equipment use, performance expectations, working patterns, health and safety, the legal rights of remote employees and who to contact for support or any concerns. |  |  | HR | Stage 4 - new normal |  |  | Access People
| Staff engagement | If an area manager normally travels across many sites or you share staff across sites consider how you can reduce this by use of technology like Zoom or Microsoft teams to limit exposure. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Staff wellbeing | Make sure staff have access to any support tools either through your organisation or a charity to protect wellbeing. | Charities such as www.mind.org.uk and www.mentalhealth.org.uk provide valuable resources. |  | HR | Stage 4 - new normal |  |  | Access People
| Staff engagement | Continue to engage and communicate as before with staff that may still be furloughed. |  |  | HR | Stage 4 - new normal |  |  | Access People
| Staff engagement | Establish a new long-term working from home policy for head office / operational staff. | Consider whether need of a physical head office space in future as possible cost saving. |  | HR | Stage 4 - new normal |  |  | Access People
| Staff wellbeing | Consider daily check-in on health and report for work log for head office staff. |  |  | HR | Stage 4 - new normal |  |  | Access People
| Payroll | Using an on-demand payment option, which enables employees to draw down on earnt pay – meaning they could get paid immediately after finishing a shift – will encourage employees to fill more shifts and reduce staff churn. |  |  | HR | Stage 4 - new normal |  |  | Access EarlyPay
| Payroll | Ensuring existing or new staff are aware of your tronc system - if it's clearly defined will help retain staff. Consider sharing tip policy with guests, too, as they may be more inclined to give a tip when they know how it’s being allocated and how it’s helping staff who spent several weeks without work. |  |  | HR | Stage 4 - new normal |  |  | Access People
| Staff management | Review outstanding leave to make sure staff have used the appropriate amount. If staff have a significant amount of untaken leave, you may want to suggest asking staff to take some during the furlough periods or / and that a percentage is taken by a certain date in the holiday year. | Remember legislation has been introduced, for relevant cases, to carry holiday leave over to the next 2 years. |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Staff management | Keep on top of any legislative and policy changes that affect your staff – there may be changes to SSP and holiday carry over. |  |  | HR | Stage 4 - new normal |  |  | Access People
| Staff levels | Monitor expected customer demand on a daily basis to ensure optimal staffing and supply levels. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Staff levels | Use labour optimisation and dynamic forecasting models within your HR and scheduling tool if available. | Make use of labour optimisation and booking data to help plan to correct staffing levels – you will want to ensure you have the right staff to still provide excellent guest experience but keep tight control of costs and not pay staff who aren’t required. |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Staff engagement | Ensure staff are aware no physical contact is permitted such as high fives and hand shakes. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Health | Put in place staff "fitness for work" checks that will need to be completed before each shift. | This could include temperature checks, confirming no coughs or feeling unwell before starting a shift. Also when available, you may require employees to obtain and carry health credentials to confirm that they've recovered from Covid-19 – dependant on Government guidance and following any contractual / data protection around mandatory measures |  | HR | Stage 2 - Pre- opening |  |  | Access People
|  | Update sickness procedure - who do staff tell if suspect they have Covid-19 and next steps. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
|  | Create process for tracking any contact between staff and customers if staff member reports Covid-19 symptoms. | It's vital that you have a record of guests and staff during all shifts if traceability is required. |  | HR | Stage 2 - Pre- opening |  |  | Access People, Access Collins
Recruitment | [5 empty] | Stage 4 - new normal
| Recruitment | With fewer hospitality roles likely to be on offer due to operators scaling back workforces, or closing sites altogether, HR managers at re-opening businesses could find themselves inundated with applications. Therefore, its important to allocate more time to effectively go through the increase in applications. |  |  | HR | Stage 4 - new normal |  |  | Access People
| Recruitment | Bear in mind that previously successful recruitment methods, such as open days, may not be possible, due to rules on mass gatherings and social distancing measures. Therefore, you'll need to come up with creative ways to find employees e.g. through video conferencing. |  |  | HR | Stage 4 - new normal |  |  | Access Screening
| Screening | Complete screening and right to work checks as quickly as possible. |  |  | HR | Stage 4 - new normal |  |  | Access People
| Screening | Conduct your Right to Work checks in line with Home Office regulations, taking note that during Covid-19 temporary adjustments have been made in obtaining documentation. |  |  | HR | Stage 4 - new normal |  |  | Access People
| Screening | Make it easier for your business with Access Right to Work mobile app and portal. Less than 5 steps to confirm if your candidate has the right to work in the UK. |  |  | HR | Stage 4 - new normal |  |  | Access People
| On boarding | Ensure that newly recruited staff can be trained quickly. If available, share online learning that can be done remotely. |  |  | HR | Stage 4 - new normal |  |  | Access LMS
| On boarding | Buddy up new starters with experienced team members during scheduling process. |  |  | HR | Stage 4 - new normal |  |  | Access People
Ramping up staff health and hygiene |  |  |  |  | Operational | Stage 2 - Pre- opening
| Health and safety | Place signage around site reminding staff to regularly to wash their hands (decide as policy on frequency of this - i.e. ever 30mins, 1hrour etc.). | Handwashing is vital to prevent transmission, ensure staff are aware and trained in the correct method and length of handwashing |  | Operational / HR | Stage 2 - Pre- opening
| Health and safety | Make sure sinks have hot running water, hand wash and either hand driers or paper towels - not cotton towels. |  |  | Operational | Stage 2 - Pre- opening
| Health and safety | Consider use of screening where possible between staff and guests. |  |  | Operational | Stage 2 - Pre- opening
|  | A reluctance to handle cash (both staff and guests) means you need to consider more contactless and other cash free payments. Is your business is equipped with all the payment tools necessary? |  |  | Operational | Stage 2 - Pre- opening |  |  | Access EPoS
| Health and safety | Add hand sanitisation stations throughout site |  |  | Operational | Stage 2 - Pre- opening
| Health and safety | Ensure guest toilets have soap and paper towels or hand dryer at all times. |  |  | Operational | Stage 2 - Pre- opening
| Health and safety | Consider use of Perspex glass or plastic at counters. |  |  | Operational | Stage 2 - Pre- opening
| Health and safety | If placing signage on the floor to show distance guests required to maintain order from printing company in plenty of time. |  |  | Operational | Stage 2 - Pre- opening
| Health and safety | Ensure team have worked out best flow for customers around site to manage social distancing and put in place appropriate signage to highlight these routes. Consider one way entrance and exit if possible. |  |  | Operational | Stage 2 - Pre- opening
| Health and safety | Sharing menus will be a no-no - consider use of disposal menus (again printing required) or going back to special board style menus or screens. |  |  | Operational | Stage 2 - Pre- opening
| Health and safety | If asking guests to sign health declaration form, ensure staff are briefed and given wording on how to handle situation. |  |  | Operational | Stage 2 - Pre- opening
| Health and safety | Identify the main routes of transmission within each site and work out what actions best support staff and guests. |  |  | Operational | Stage 2 - Pre- opening
| Site cleanliness | Organise site deep clean to be completed and recorded prior to opening. |  |  | Operational | Stage 2 - Pre- opening
| Site cleanliness | Agree new cleaning rota to meet guidelines (once set out). | Include frequency, areas to be cleaned and specific tasks. Include any items customers may have access to such as tables, salt and pepper pots etc. |  | Operational | Stage 2 - Pre- opening
| Site cleanliness | Ensure staff allocated to cleaning roles for each shift. |  |  | Operational | Stage 2 - Pre- opening
| Site cleanliness | Display updated staff cleanliness information for customer reference. |  |  | Operational | Stage 2 - Pre- opening
| Site cleanliness | Allocate point of contact for each shift to answer any customer question or queries re cleanliness and staff hygiene. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access People
| Site cleanliness | Decide on new cleaning / sanitising regime for items shared between guests such as payment keypads, salt and pepper pots (if still using), or move to disposable sachets. |  |  | Operational | Stage 2 - Pre- opening
| Site cleanliness | Consider installing sanitizer dispensers, touchless if possible, at guest and staff entrances and contact areas. |  |  | Operational | Stage 2 - Pre- opening
| Site cleanliness | Allocate member of team to keep track of Covid-19 secure guidelines (Government issues guidelines) and any changes that happen in lead up to reopening. |  |  | Operational | Stage 2 - Pre- opening
| Site cleanliness | Consider use of facemasks and gloves for staff in line with scientific evidence of the moment - but also for customers? |  |  | Operational | Stage 2 - Pre- opening
| Site cleanliness | Set rules about how often items used by multiple guests will need to be sterilised e.g. will you wipe down card keypad after every use, every 15mins etc. |  |  | Operational | Stage 2 - Pre- opening
| Site cleanliness | Follow Government guidelines in terms of detergent to be used in the kitchen. |  |  | Operational | Stage 2 - Pre- opening
| Supplier | Put in place a policy for deliveries - will you enforce temperature checks and declaration forms if delivery drivers enter premises? |  |  | Operational | Stage 2 - Pre- opening
| Personal Protective Equipment | HR managers will need to work with health and safety (if this is a separate department) to ensure Government guidelines on work practices are upheld and may even be involved in sourcing PPE, like face masks or gloves. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| New working practices | Ensure that staff being re-integrated into the workforce, understand any new working practices; an area that will certainly need more attention than previously. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Delivery & takeaway | Consider how to keep click and collect customers away from guests dinning in. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Delivery / Click & Collect
| Delivery & takeaway | If using delivery provider do not allow delivery drivers onto site - arrange for staff to take food and maintain 2 meter distance. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Delivery / Click & Collect
| Delivery & takeaway | Do not offer whole menu for delivery customers - shorten to dishes that travel best and deliver good margins. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Delivery / Click & Collect
| Contractors | Formalise new process for when external contractors arrive on site - engineers already need to confirm they have completed certain checks such as undertaking their risk assessment, but we would consider expanding on this and include checks such as washing hands etc. |  |  | Operational | Stage 2 - Pre- opening
| Risk Assessment plan | Put in place an individual risk assessment for each site confirming how you are meeting any new Government guidelines to keep your staff and customers safe. | This should include how you will monitor customer toilet usage to ensure social distancing regulations met. |  | Operational | Stage 2 - Pre- opening
| Monitor, track and report | Consider how you will monitor, track and report on new site cleaning and health and safety and risk management procedures both at site and group level. | Being able to report and identify gaps will be critical to ensure compliance with new HSE guidelines and provide evidence if and when required. |  | Operational | Stage 2 - Pre- opening |  |  | Access Health & Safety
Onsite social distancing |  |  |  |  | Operational |  |  |  | Access Collins
| Altering tables and floorplans | Once exact Covid-19 secure guidelines released on acceptable distance of tables within sites, rework table layouts for each site to maximise guest numbers. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Altering tables and floorplans | Check table capacity if available within a booking tool to define new layout. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Altering tables and floorplans | Check order of tables once layout is reviewed so make it easy to view and manage format. If possible within your booking tool drag inactive tables to the bottom of the list and close them. | Don't delete tables as hopefully you'll be able to reintroduce again soon. |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Altering tables and floorplans | Reorder floorplan by dragging tables in use into the new positions. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Altering tables and floorplans | Test any changes to booking features to ensure updates are correctly updating on the widget within website. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Altering tables and floorplans | Ensure staff are familiar with new layout, table numbers and how to navigate within safety guidelines. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Keep on top of guest numbers | Consider shutting off same day bookings to ensure you can easily manage daily intake of covers. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Keep on top of guest numbers | If you don't have booking technology in place, review asap as this will be the best tool to ensure staff stay on top of guest numbers and manage enquiries / bookings and still meet social distancing regulations. | Many tools enable guests to book via a widget on your website, 3rd party sites and social channels. |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Keep on top of guest numbers | If available within a booking tool ensure staff are training and regularly checking "Heads in" feature to monitor total number of heads in venues at any one time. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Keep on top of guest numbers | Try to limit arrivals - so you can stagger guests between certain times throughout day and stagger flow of customers more easily. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Reduce staff / guest interaction | Reduce staff / guest interaction as much as possible by considering technology such as order and pay at table. | Benefits of this technology are not just for guests, but it helps safeguard staff too. Guests use their own phone with no app required and they can pay without having to touch a keypad used by other guests. |  | Operational | Stage 2 - Pre- opening |  |  | Order and pay - Access EPOS
| Reduce staff / guest interaction | Offering guests the ability to pre-order where possible takes away initial waiting for drinks at bar and reduces staff / guest interaction. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Reduce staff / guest interaction | Look at closing off specific areas to bookings and keep area for walk-ins. | Bearing in mind walk-ins may be down depending on location - i.e. if central London lunch trade or tourist area. |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Booking policy | Update booking policy or add specific message to returning guests before they make a booking or enquiry. | If tables need to be 2metre or 6ft for example add a simple message along lines of "Booking policy: We are following the Government Covid-19 secure guidelines on social distancing and placing tables 6feet apart at all times". |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Booking policy | Update any email templates with your booking policy re social distancing to offer reassurance. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Booking policy | Consider a review of automated bookings process. You may want to move from automated booking to enquiry only to give more operational control. | This is useful to allow you to open only when enquiries are at a sufficient level or you're confident walk-ins will cover gaps needed to pay staff costs. |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Pre-payments | Consider implementing pre-payments, deposits or card authentications | Helps minimise impact of no shows and you can set minimum spend if wish to drive up spend per head. |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Booking policy | If new policy is not to accept walk-ins ensure GMs and front of house have tools to manage difficult conversations with customers. Not just training but signage to back up decision and use clear communications through digital and social channels. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Onsite traffic management | Consider the use of floor marking to indicate spacing required, particularly in crowed areas. |  |  | Operational | Stage 2 - Pre- opening
| Onsite traffic management | Introduce one way movement if viable. |  |  | Operational | Stage 2 - Pre- opening
|  | Consider expanding outdoor seating if viable. | Local councils may be easing restrictions and permits to allow more outdoor dining. |  | Operational | Stage 2 - Pre- opening |  |  | Access Collins
| Check-in hotel guests | Make sure social distancing advice is clear on entrance to the building and provide adequate waiting space at reception. |  |  | Operational | Stage 2 - Pre- opening
| Check-in hotel guests | Communicate with guests in advance to ensure guests are aware of additional health and safety practices/ |  |  | Operational / Marketing | Stage 2 - Pre- opening |  |  | Access Collins
| Check-in hotel guests | Any shared items such as pens and chip and pin machines should be disinfected before the next guest uses them. |  |  | Operational | Stage 2 - Pre- opening
Procurement
| System checks | Have you closed down - stock, waste - have you written stock off? |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Procure Wizard
| System checks | Reactivate any users on procurement system (if applicable). |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Procure Wizard
| System checks | Are your financial periods up-to-date? |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Financials
| System checks | Check order status - were orders left open or closed down as lockdown was implemented? |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Procure Wizard
| Supply chain | Are your suppliers still trading - reach out to them. |  |  | Finance / Procurement | Stage 2 - Pre- opening |  |  | Access Procure Wizard
| Supply chain | Check on ordering system if suppliers are operating. What they have and if there are any items not in stock or limited supply, may need to consider substituting products with replacements as required. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Procure Wizard
| Supply chain | Check on ordering system if delivery dates are as per business as usual or taking longer. Place orders to arrive in plenty of time. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Procure Wizard
| Pricing | Are there any product price changes with suppliers? |  |  | Finance | Stage 2 - Pre- opening |  |  | Access Procure Wizard
| Allergen | Check if there any changes to allergens that staff need to be made aware of? |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Procure Wizard
| Supplier deliveries | If goods can't be delivered before or after guests are onsite then ensure separate space for deliveries so guests not impacted. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Procure Wizard
Stock & waste checks
| Stocktake | Completed new stocktakes as required. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Procure Wizard, Access EPoS
|  | Did you closed previous stocks? |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Procure Wizard, Access EPoS
|  | Did you record all wasted products prior to closing? |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Procure Wizard, Access EPoS
|  | Will your new stock window be looking at last close? |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Procure Wizard, Access EPoS
Stock levels vs bookings and restricted operating |  |  |  |  | Finance / Board / HR
|  | Decide on % of food and % of beverage sales forecast expected to enable food ordering. Taking into account any new channels such as delivery, retail you may have already started or plan to start. |  |  | Board | Stage 2 - Pre- opening |  |  | Access Procure Wizard
|  | Daily sales reports via POS to drill down on best selling items and see which team member is selling the most of particular items. |  |  | Finance | Stage 3 -Opening week (and beyond) |  |  | Access Procure Wizard, Access EPoS
|  | Weekly management P&L reporting via POS to analyse weekly sales and review against budgets / target sales (including petty cash, complementaries and discounts). |  |  | Finance | Stage 3 -Opening week (and beyond) |  |  | Access EPoS
|  | Time zone reports via POS to dig down into the most popular trading slots throughout your day. |  |  | Finance | Stage 3 -Opening week (and beyond) |  |  | Access EPoS
|  | Optimum GP% report to ensure theoretical GP% are on target based on your product costs and sales mix. |  |  | Finance | Stage 3 -Opening week (and beyond) |  |  | Access Procure Wizard, Access EPoS
| Training | Arrange team training required on above if required. |  |  | HR | Stage 3 -Opening week (and beyond) |  |  | Access People
Focus on guest experience
| Staff training | Pre-opening make sure team leaders / trainer are prepared to get staff ready when doors open. |  |  | HR | Stage 2 - Pre- opening |  |  | Access People
| Staff training | Ensure staff are prepped, trained and ready to deliver service of their life. No more than ever is time to exceed guest experience to encourage return visits and recommendations. |  |  | HR | Stage 3 -Opening week (and beyond) |  |  | Access People
| Improve queuing experience | Consider tools that offer ability for guests to join virtual queues. | This helps meets social distancing guidelines, is a much better experience for guests and means tables are turned quicker. |  | Operational | Stage 3 -Opening week (and beyond) |  |  | Access Collins
| Elevate experience | With the "hospitality" element of the sector impacted by social distancing consider way to augment the users experience. Get input from customers and guests on what things would help create right atmosphere whilst adhering to restrictions. |  |  | Operational | Stage 3 -Opening week (and beyond)
Cash flow
|  | Make sure all tills have opening float. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access EPOS
|  | Make a decision on payment methods you will accept e.g. going cashless may help prevent the spread of germs and help protect staff and customers alike. |  |  | Board | Stage 2 - Pre- opening |  |  | Access EPOS
|  | Review which merchants/POS using - look at merchant processing times as this may impact cash flow if waiting 3-5 working days to hit your bank account. |  |  | Board | Stage 2 - Pre- opening |  |  | Access EPoS
|  | If you have been selling vouchers decide if minimising number of vouchers that can be used on a given day/night as this also impacts cash flow. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access SODA
|  | If you are doing delivery check T&C's aren't going to change if using third party such as Deliveroo, Just Eats etc. |  |  | Operational | Stage 2 - Pre- opening
| Bookings | Make sure you can achieve maximum number of booking possible whilst still adhering to social distancing guidelines by ensure your venues are appearing on appropriate websites. |  |  | Marketing | Stage 3 -Opening week (and beyond) |  |  | Access Collins
| Upselling | Use pre-ordering technology to help upselling and can be used to set minimum spend. |  |  | Operational | Stage 3 -Opening week (and beyond) |  |  | Access EPoS
| Upselling | Ensure staff are trained in upselling and using every opportunity to (delicately not in a pushy way) encourage more upselling. |  |  | HR | Stage 3 -Opening week (and beyond) |  |  | Access People
| Upselling | Consider staff incentives for front of house staff who deliver most upsell each week / month. |  |  | HR | Stage 3 -Opening week (and beyond) |  |  | Access People
| Voucher redemption | Consider how you manage voucher redemption in the first week and beyond to maximise cash flow into the business. You may want to restrict number of vouchers used each for a period of time. |  |  | Operational | Stage 3 -Opening week (and beyond) |  |  | Access SODA
| Staff payments | You may see an increase in requests for staff advances in those early weeks with limited cash flow to support. Consider technology to support such as on-demand payment which has no costs to operators. |  |  | Operational | Stage 3 -Opening week (and beyond) |  |  | Access EarlyPay
|  | Review expenses policy and consider reducing number of approvers to ensure this is channelled to one to two people to have tighter control on outgoings |  |  | Finance | Stage 3 -Opening week (and beyond) |  |  | Access Financials
|  | Repairs and property maintenance is often area of overspend, use technology or funnel approval - in advance - to small team to keep tight control on costs. |  |  | Finance |  |  |  | Access Maintain
Menu Engineering
|  | Start reviewing menus with chefs as soon as possible as you'll need to speed up menu development process. | If requirement is to social distance within kitchen what new menu will enable less chefs onsite during each shift to deliver. Benefits of reduced menu will be less food wastage, lower chef labour bills and ensuring meeting social distancing requirements. |  | Operational / Head Chef | Stage 2 - Pre- opening |  |  | Access Procure Wizard
|  | Plan for disruptions to supply chain - be flexible with ingredients if they've hard to get hold of or come from abroad. |  |  | Operational / Head Chef | Stage 2 - Pre- opening |  |  | Access Procure Wizard
|  | Make sure you have a strong Inventory management process in place in order to achieve food cost control. Reviewing your current processes to track stock-in and stock-out and daily consumption will help identify and ultimately reduce wastage. |  |  | Operational / Head Chef | Stage 5 - longer term |  |  | Access Procure Wizard, Access EPoS
|  | Look at tools that can generate real time reports on stock levels removing the problem of over ordering (critical to help manage cash flow) or under-ordering. |  |  | Finance | Stage 2 - Pre- opening |  |  | Access Procure Wizard, Access EPoS
|  | Collecting and analysing data of all sales over past six months before Covid-19 will enable you to compare sales for each dish and remove any underperforming dishes to reduce food costs. |  |  | Finance | Stage 5 - longer term |  |  | Access Procure Wizard, Access EPoS
|  | Review portion control to help reduce wastage. Ensuring the right plating of food can help reduce food prices and wastage; things to track include food returned by the customer and extra portions being thrown away. |  |  | Head Chef | Stage 5 - longer term |  |  | Access Procure Wizard
|  | If previously offered a buffet temporarily remove this service as risk of cross contamination is too high. |  |  | Operational | Stage 2 - Pre- opening
|  | Any tableside food preparations such as food item selection dessert carts and conveyor belts should be reconsidered for foreseeable future. |  |  | Operational | Stage 2 - Pre- opening
Control your costs |  |  |  |  | Head Chef/ Finance
| Analysis | Schedule time to do an analysis on your menu after first few days / first week - which menus are performing, are you hitting GP? |  |  | Head Chef/ Finance | Stage 3 -Opening week (and beyond) |  |  | Access Procure Wizard
| Analysis | Get hold of as much data as possible to gain insights to costs vs profits in first few weeks. |  |  | Finance | Stage 3 -Opening week (and beyond) |  |  | Access Procure Wizard
| Stock | Manage stock levels to ensure not over ordering. |  |  | Head Chef | Stage 3 -Opening week (and beyond) |  |  | Access Procure Wizard, Access EPoS
| Processes | Review existing processes - identify areas that may not be cost effective e.g. food waste, paying unnecessary high prices (without compromising quality). |  |  | Operational | Stage 3 -Opening week (and beyond) |  |  | Access Procure Wizard
| Financial management | If you deactivated standing orders review these now. | Look at whether you need to adjust values / volumes when reactivating. |  | Finance | Stage 3 -Opening week (and beyond) |  |  | Access Financials
Supplier support
|  | Reach out to key suppliers to ensure the team are all set up correctly on all the systems they will be using e.g. do passwords need to be reset? |  |  | Operational | Stage 3 -Opening week (and beyond)
|  | Give GMs checklist for passwords, business sheet data, stock results, hardware status. |  |  | Operational | Stage 3 -Opening week (and beyond)
|  | Ensure support info and user guides are at hand for all staff. |  |  | Operational | Stage 3 -Opening week (and beyond)
|  | Ensure staff have easy route to central contact within group in order to raise technology issues and request suppliers to help with day to day operations. | Such as menu updates, data imports, margin controls and stock analysis, system health checks etc. |  | Operational | Stage 3 -Opening week (and beyond)
PROPERTY MAINTENANCE
| Compliance | Review compliance position immediate and schedule in any statutory service visits that could not take place during lockdown. | This is particularly key if you operate in certain locations such as shopping centres or airports, it is especially critical to be compliant and legal. |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Contractors | Review your contractor base to ensure they have coverage across all trades and areas of the country, especially for business critical pieces of equipment. | Some suppliers may no longer be in business so ensure you have coverage as needed to support reopening and beyond. |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Lift usage | Think about how to minimise any lift usage. Provide disinfectant or wipes to enable guests and staff to safely touch control panels |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Lighting | Switch on lights gradually to avoid power spikes. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Pest control | Check all traps for signs of activity and report via a property maintenance tool or pest control if there are any issues. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Cellar cooling | • If left on, check the temperature. • If left off, switch on and monitor the temperature as it may take up to 24 hours to reach 11 to 13F depending on the design, installation and brand of equipment. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Beer dispense | Switch on beer coolers and gas system. • Clean lines. • flush lines with water. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Cold (fresh water) | Open all cold taps and allow water to run for 5 to 10 minutes at a medium flow, for example, not fully open. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Gas | Check gas lever at the mains is on and check gas lever/switch to the kitchen and individual items are on. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Hot water cylinders and boilers (hot water pumps and radiators) | • If left on, run taps for 5 minutes and check temperatures at taps and radiators. • If left off, switch on and after two to three hours run taps and check temperatures (and if heating required check radiators). |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Air conditioning | Very much dependent on what kit is installed within your site, but as a general rule turn on the various units gradually and allow to run for an hour or so. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Kitchen extraction | Check the interlock box is powered and not showing a fault. If it is in fault the gas emergency stop button might be pushed in, if so, pull it out and twist slightly (depends on the model): • Set the speed controller (if fitted) to a slow speed and • Switch on gradually, over 5 to 10 minutes turn up the speed to just below maximum and let it run for a few minutes and then set it to your normal set speed. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Walk-in freezers / fridges | If left on, check temperatures and stock condition and if left off, presumably empty stock, clean thoroughly and switch on (step by step, not all at once), freezer may take up to 12 hours to reach temperature. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Bar bottle cabinets | If left on, check temperatures and if left off, switch each one on gradually and check temperatures. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Fridges / freezers (Kitchen etc.) | If left on, check temperatures and stock condition and if left off, clean thoroughly and switch each one on gradually, check temperatures. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Dish and glasswashers | Ensure they are fully cleaned inside, all parts put back together including drain plugs and run through 2 to 3 wash cycles empty. See below for more detailed advise from CrystalTech. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Ice machines | If left on and the bin is full and closed, check ice condition. Clean and sanitise the bin and switch on, it will take up to 24 hours to fill a large machine bin. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Electrical items | For everything from kitchen equipment to music systems, turn on gradually. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Coffee machine | For all types of machines, check the water is connected and switch on the power. • For fully automatic B2Cup machines, fill with fresh beans and milk, and once heated up make around 5 to 6 coffees and discard them. • For traditional machines, flush water through the group heads for 3 to 4 minutes and open the steam valves whilst the machine is heating up. Once steam appears, close the valves. After 20 minutes check the pressure gauge is at 1 to 1.3 bar, open the steam valves checking pressure stays at around 1 bar. Fill the grinder with fresh beans and make some coffees. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
| Fire alarms / emergency lights | Conduct your normal weekly and monthly tests and report any issues via property maintenance tool or head office as relevant. |  |  | Operational | Stage 2 - Pre- opening |  |  | Access Maintain
Getting customers through the door
| Direct marketing | Reach out to recently cancelled bookings to encourage rebooking's. |  |  | Marketing | Stage 2 - Pre- opening |  |  | Access Collins
| Direct marketing | Start marketing to customer database to tell then when you'll be opening. If doing launch event promote tickets well in advance of reopening date. |  |  | Marketing | Stage 2 - Pre- opening |  |  | Access Collins, Access Tonic
| Make it special | Think about opening day & week. Do you want to host launch event to increase spend per head? You could sell tickets and make a special event and this would also help you manage numbers effectively. |  |  | Marketing | Stage 2 - Pre- opening |  |  | Access Collins, Access Tonic
| Promotion | Ensure your venue/s are appearing on all key sites such as Designmynight.com, TripAdvisor, VisitBritain etc. |  |  | Marketing | Stage 2 - Pre- opening |  |  | Access Collins
|  | Consider using GoogleReserve if not already using - it allows guests to book or enquiry directly from Google listing or Google maps. |  |  | Marketing | Stage 2 - Pre- opening |  |  | Access Collins
| Social media | Any steps you can take to start increasing social media posts announcing when you're opening will help create noise (appreciate it may be difficult to ramp up with staff still furloughed). |  |  | Marketing | Stage 2 - Pre- opening
| Offers | Consider offers with caution but a thank you to NHS workers or key workers could help drive guests and give something back at the same time. |  |  | Marketing | Stage 2 - Pre- opening
Marketing
|  | Plan simple marketing campaign for duration of opening weeks (not just in the build up). |  |  | Marketing | Stage 3 -Opening week (and beyond)
|  | Ensure continued adherence to GDPR. |  |  | Marketing | Stage 3 -Opening week (and beyond)
|  | If new vision and values agree pre-opening work plan to ensure all marketing campaigns support vision. How will this impact creative, content, social media message. It's not a case of quick update - look to develop deeper relationship with customers. |  |  | Marketing | Stage 3 -Opening week (and beyond)
|  | Focus on community in messaging especially if you've received a lot of support during lockdown. |  |  | Marketing | Stage 3 -Opening week (and beyond)
|  | Focus on areas public will have missed; fresh produce, getting out of the house, pub/bar/restaurant ambiance that's been missed, outdoor spaces for those without gardens or balconies and the key social point - spending time with family and friends! | Brand story if reviewed in pre-opening! |  | Marketing | Stage 3 -Opening week (and beyond)
|  | Avoid discounting to attract customers as this won't help sustain long-term profit or loyal customers - you could consider limited offers for key workers. |  |  | Marketing | Stage 3 -Opening week (and beyond)
| Deeper engagements | Time to focus on brand story rather than light touch content and images. If you can get guests and local community more engaged with brand then likely to become much more connected. |  |  | Marketing | Stage 3 -Opening week (and beyond)
| Measurement | Make sure marketing team have clear objectives, KPI and can show return on any investment. |  |  | Marketing | Stage 3 -Opening week (and beyond)
|  | Ensure your marketing and management teams have got instant access to booking information at site, region and group level. | This enables you to direct campaigns and budget to support sites and regions that need it most to achieve maximum ROI. |  | Marketing | Stage 3 -Opening week (and beyond) |  |  | Access Collins
|  | Use existing customer data from within booking tools to personalise messages and encourage return visits. | Spending time and effort generating booking enquiries is wasted if your internal conversion rates are poor. Enquiry management technology enables your team to access enhanced tracking and reporting tools, improving conversions rates dramatically. |  | Marketing | Stage 3 -Opening week (and beyond) |  |  | Access Collins
|  | Ensure conversion rate is a good as can be to successful generate as much footfall as possible. |  |  | Marketing | Stage 3 -Opening week (and beyond) |  |  | Access Collins
|  | Define your media strategy - how are you going to deal with worst case scenario if staff or customers that visits venues has Covid-19? It's best to be prepared and make sure communication is kept transparent at all times. |  |  | Marketing | Stage 3 -Opening week (and beyond)
Financial Management
|  | Use accurate and timely data to monitor business performance. |  |  | Finance | Stage 4 - new normal |  |  | Access EPoS
|  | Review sales data at the end of every day, not weekly - in order to identify problem sites or underlying issues quickly. |  |  | Finance | Stage 4 - new normal |  |  | Access Workspace
|  | Be prepared to manage cash flow when any Government or bank lifelines end and negotiate extended payment terms where possible, so that financial commitments to staff, suppliers, etc. can be controlled. |  |  | Finance | Stage 4 - new normal |  |  | Access Financials
|  | Review operator / landlord business model during planning. |  |  | Finance | Stage 4 - new normal |  |  | Access Financials
|  | Review each cost item for savings and plan for possible increase in some areas. |  |  | Finance | Stage 4 - new normal |  |  | Access Workspace
|  | Balance sheet review - to include considering raising new equity, no dividends short to long term. |  |  | Finance | Stage 4 - new normal |  |  | Access Financials
|  | Complete review of Capex costs. |  |  | Finance | Stage 4 - new normal |  |  | Access Financials
|  | Consider a restructure or CVA if allows better negotiation with landlords and debtors. |  |  | Finance | Stage 4 - new normal |  |  | Access Financials
|  | Board review of any options to de-risk business. |  |  | Board | Stage 4 - new normal |  |  | Access Financials
|  | Model out different shape recovery - V, U or both shapes. |  |  | Board | Stage 4 - new normal |  |  | Access Financials
|  | Can you defer any bills, re-opening costs? |  |  | Finance | Stage 4 - new normal |  |  | Access Financials
|  | Model how to stretch working capital to fund short term gaps. |  |  | Finance | Stage 4 - new normal |  |  | Access Financials
| Reporting | Keep HO up-to-date with daily data broken down by site, region and company wide as applicable, to ensure margins are being managed correctly. |  |  | Finance | Stage 4 - new normal |  |  | Access Workspace
| Consider types of trade | If you have certain sites that are reliant on foreign tourism, where there is likely to be a decline in this type of trade, then take this into account when forecasting. |  |  | Finance | Stage 2 - Pre- opening |  |  | Access Financials
| Keep control of costs | Getting on top of your cash inflow has never been more critical. If historically your team provide sales data every few days or weekly and it’s a manual process (prone to errors and inaccuracy) now might be the time to upgrade EPOS and reporting technology to ensure you have this business intelligence available instantly. |  |  | Finance | Stage 5 - longer term |  |  | Access EPoS
| Keep control of costs | Keeping on top of over-performing and under-performing sites on a daily basis ensures help can be provided quickly where needed, before the situation deteriorates too quickly. |  |  | Finance | Stage 5 - longer term |  |  | Access Workspace
| Keep control of costs | Monitoring and having full control over operational expenses at site level will have a positive impact on GP. |  |  | Finance | Stage 5 - longer term |  |  | Access Workspace
| Keep control of costs | Potentially look to track and review data on a more regular basis than historically . | Track what specifically e.g. daily takings, costs (labour, maintenance, supplier, etc.) and how regularly? |  | Finance | Stage 2 - Pre- opening |  |  | Access Workspace
| Keep control of costs | Get real-time BI of each site's cash inflow (what specifically is cash inflow?). |  |  | Finance | Stage 2 - Pre- opening |  |  | Access Workspace
| Keep control of costs | Track and record daily sales figures for each site to spot any early signs of intervention needed. |  |  | Finance | Stage 2 - Pre- opening |  |  | Access Workspace
| Keep control of costs | Where sites are over-performing, share best practice across sites. |  |  | Finance | Stage 2 - Pre- opening |  |  | Access Workspace
| Insurance | Check your insurance arrangements to ensure you have appropriate cover in place and notify your broker / insurance provider of the plans to return staff to the workplace. |  |  | Finance | Stage 2 - Pre- opening |  |  | Access Financials
| Cost-cutting | Dependant on how the furlough scheme may change / expire, you many need to consider possible cost-cutting steps in order to ensure longer-term sustainability; such as reducing pay and /or hours, offering unpaid or part-paid sabbaticals and in extreme cases, redundancies. | If considering redundancies, you'll need to bear in mind the required consultation obligations. |  | Board | Stage 5 - longer term |  |  | Access Financials
Adapting your business model
|  | Take some time to review your business model - doing what you did pre-covid may not work? With potentially more people working remotely post Covid-19, your business may need to start adapting to this new reality. Is your business ready for this? It’s clear that operations offering an Omni- channel strategy including a mixture of delivery, on-premise, click and collect, event catering or DIY recipe packs are more likely to recoup cash flow more quickly. |  |  | Board | Stage 5 - longer term |  |  | Access Workspace
|  | If you’re new to delivery you might need to consider developing your menu to be takeaway friendly? Many businesses already offer delivery service as core to their proposition however, can you improve or maybe even re-invent this market? |  |  | Board | Stage 5 - longer term |  |  | Access Delivery / Click & Collect
|  | Look at your current systems to ensure any transition is seamless to your business and customers |  |  | Board | Stage 5 - longer term
|  | As we discussed above consumer habits may have changed for short term or long term after the lockdown period, so with more time available expanding beyond a pure on premise offering may be a viable future strategy. |  |  | Board | Stage 5 - longer term
New landscape
| Strategy | Weekly review of competitor landscape - businesses opening, closing to be able to react and predict impact on business. Do by region if possible. | How will their actions affect your trade and how can you respond? The closure of a big office base or shopping hub may reduce footfall in the area, or closure of a competitor may open up opportunities to attract new customers. |  | Board | Stage 3 -Opening week (and beyond)
| Strategy | Monthly review of Customer behaviour - use booking and transaction data from your estate but also sector data to get full 360 view. | Elements to consider include the frequency, length or timing of visits to hospitality venues altering. Watch and listen so you’re ready to respond to any pattern that emerges and update stock ordering and staffing levels appropriately |  | Board | Stage 3 -Opening week (and beyond) |  |  | Access Collins, Access EPoS
Be Prepared
|  | Keep constant review of business over coming weeks and months to enable you to be agile and respond. | There’s likely to be a steady shift in attitude and behaviours whilst things shake down and we shape our new normal - those who monitor will be in a better position to adapt. |  | Board | Stage 3 -Opening week (and beyond) |  |  | Access Workspace
|  | Keep engaged with relevant counterparts and peers | The hospitality sector has come together so continue to lean on and talk to peers to share learnings, best practices and tips to get through this together. |  | Board | Stage 3 -Opening week (and beyond)
|  | Consider festive season -how is Covid-19 going to impact most profitable few months on the year. Start to consider now if you'll more private dining space, will you offer Christmas party deliveries so corporate guests can manage own health and safety but you provide food and drink? |  |  | Board | Stage 3 -Opening week (and beyond)

## Useful resources
Topic | Links
UKHospitality - up to date coronavirus information for hospitality businesses | https://www.ukhospitality.org.uk/general/custom.asp?page=coronavirus
GOV.UK - Business rates relief | https://www.gov.uk/apply-for-business-rate-relief
GOV.UK - Financial support for businesses during coronavirus (COVID-19) | https://www.gov.uk/government/collections/financial-support-for-businesses-during-coronavirus-covid-19
GOV.UK - Complete ban on evictions and additional protection for renters | https://www.gov.uk/government/news/complete-ban-on-evictions-and-additional-protection-for-renters
Local Authority Discretionary Grants | https://www.gov.uk/guidance/apply-for-the-coronavirus-local-authority-discretionary-grants-fund
GOV.UK - Coronavirus (COVID-19): what you need to do | https://www.gov.uk/coronavirus
Institute of Hospitality - Guidance and support during the coronavirus crisis | https://www.instituteofhospitality.org/guidance-and-support-during-the-coronavirus-crisis/
The Caterer - Coronavirus advice hub for hospitality operators and employees | https://www.thecaterer.com/business/advice/coronavirus-advice-hub
The Caterer – Dealing with your landlord | https://www.thecaterer.com/news/advice-coronavirus-dealing-landlord
Big Hospitality – Coronavirus hub | https://www.bighospitality.co.uk/Article/2020/05/01/Coronavirus-the-positive-hospitality-industry-moves